## Content Plan Template
OPEN TEXTBOOK CONTENT PLAN
This spreadsheet is a template for your open textbook. The Front Matter is an example of how this plan should be used. Feel free to tailor the templete to your needs by changing the values and adding additional rows and columns as see fit. Essential chapters for each textbook are highlighted in bold.
Textbook Name: |  |  |  | Course code:
Link to your open textbook draft:
Start Date of Project |  |  |  | Pilot Date:
| Assigned to | Progress | Start Date | End Date | Tasks | Updates | Before publishing (ex. Adhere to the Accessibility Checklist? Is the design consistent? Has it been proof read per your style guide?
FRONT MATTER
Introduction | Rachel | 95% | 2025-06-11 |  | Needs to be proofread. | Almost completed
Authors | David | 50% | 2025-06-11
Accessibility Statement | John | 15% | 2025-06-12 |  | Link to Accessibility Page
Acknowledgments | Sam | 100% | 2025-05-15 | 2025-06-09
BODY SECTION
PART 1 | Pressbooks Examples
A Departmental Approach |  | 0%
Varied Approaches |  | 0%
External Examples |  | 0%
PART 2 | Video Tutorials
How to Use Pressbooks |  | 0%
Exploring Pressbooks Features |  | 0%
PART 3 | Your PART title
Part 3: Chapter 1 title |  | 0%
Part 3: Chapter 2 title |  | 0%
BACK MATTER
Versioning Page |  | 0%